FIN CREADOR

# Product & Sprint Plan

Web • Android • iOS

A delivery roadmap built around one principle: every sprint ends with a tested, usable feature—not just setup work or static screens.

| Planning item | Decision |
| --- | --- |
| Planning horizon | 12 two-week sprints • approximately 24 weeks |
| Initial release | MVP after Sprint 5, then staged feature releases |
| Platforms | Responsive web app + Android and iOS apps |
| Core principle | One backend, consistent financial rules, security from Sprint 1 |

# 1. Executive summary

Fin Creador is a personal finance platform for recording daily expenses and income, understanding cash flow, tracking investments, planning future expenses, and receiving reminders and insights. Build the everyday money-tracking core first, then add planning, portfolio management, AI, notifications, and production hardening.

Track expenses and income by day, week, month, year, and custom date range.

Manage salary, rent, freelance/business income, cash, bank accounts, and other sources.

Plan goals such as travel, a car, a bike, a home, and an emergency fund.

Track shares, mutual funds, ETFs, deposits, liabilities, and net worth.

Offer optional AI explanations based on verified user data.

Send configurable reminders, including an optional 10 PM expense reminder.

# 2. Recommended technical baseline

| Area | Recommendation |
| --- | --- |
| Web | Next.js App Router, React, TypeScript, Tailwind CSS, shadcn/ui |
| Mobile | React Native with Expo for Android and iOS |
| Backend | Supabase, PostgreSQL, Supabase Auth, server-side functions |
| Security | Row Level Security (RLS), server-side validation, secret management |
| AI | Server-side provider abstraction; code calculates, AI explains |
| Notifications | Scheduled delivery, Expo push, supported web notifications |
| Quality | Git branches/PRs, migrations, automated tests, lint, typecheck, build |

Preserve the existing repository and working conventions. Inspect before restructuring; do not force a new architecture onto working code.

# 3. Sprint roadmap at a glance

| Sprint | Timeline | Focus | Usable outcome |
| --- | --- | --- | --- |
| 1 | Weeks 1–2 | Foundation, authentication & profile | Register/sign in; manage profile. |
| 2 | Weeks 3–4 | Accounts & starting balances | Create bank, cash, savings, and other accounts. |
| 3 | Weeks 5–6 | Expense & transaction tracking | Add, edit, search, filter, and review transactions. |
| 4 | Weeks 7–8 | Income sources & recurring items | Track multiple income sources and recurring entries. |
| 5 | Weeks 9–10 | Dashboard & analytics | View meaningful time-based financial insights. |
| 6 | Weeks 11–12 | Budgets & savings goals | Plan targets and track progress. |
| 7 | Weeks 13–14 | Investment portfolio | Track holdings and manual valuations. |
| 8 | Weeks 15–16 | Loans, liabilities & reports | View liabilities, net worth, and export records. |
| 9 | Weeks 17–18 | AI financial insights | Get explanations grounded in verified data. |
| 10 | Weeks 19–20 | Notifications & reminders | Configure reminders and upcoming-payment alerts. |
| 11 | Weeks 21–22 | Mobile polish, offline & PWA | Harden supported offline and cross-platform workflows. |
| 12 | Weeks 23–24 | Security & production release | Release candidate ready for deployment/store submission. |

# 4. Sprint detail and acceptance criteria

## Sprint 1 — Foundation, authentication and profile

Weeks 1–2 | Usable outcome: A user can create an account, sign in, and manage their profile.

### Scope and deliverables

Inspect repository, routes, dependencies, migrations, auth setup, and tests before changing anything.

Set up environments, migration conventions, CI checks, and web/mobile application shells.

Implement email/password, Google OAuth, password recovery, sign-out, and session handling.

Add profile editing, currency, country, and time-zone preferences; default to India, INR, Asia/Kolkata.

Plan Apple sign-in where required by iOS distribution/authentication setup.

### Acceptance criteria

Sign-up, sign-in, sign-out, and recovery flows work with clear errors.

Profile changes persist after a fresh login.

Baseline RLS and server authorization are implemented and tested.

No service-role or provider secrets appear in client bundles.

Local setup and test deployment are documented.

## Sprint 2 — Accounts and starting balances

Weeks 3–4 | Usable outcome: A user can create accounts and see where their money is held.

### Scope and deliverables

Support bank, cash, savings, and other account types.

Add opening balances, account names, optional institution/labels, and currency.

Implement create, edit, archive, and balance views.

Add constraints, indexes, ownership checks, and RLS tests.

### Acceptance criteria

Account CRUD works for an authenticated user.

Users cannot read or modify another user’s accounts.

Money uses exact representations, not binary floating point.

Archived accounts do not corrupt historical reports.

Dependencies: Sprint 1 authentication and database foundation.

## Sprint 3 — Expense and transaction tracking

Weeks 5–6 | Usable outcome: A user can maintain a reliable daily transaction ledger.

### Scope and deliverables

Add expenses and income with amount, date, category, account, and optional note.

Add transfers between the user’s accounts.

Support edit, delete/safe reversal, search, date/category/account filters, and recent history.

Build fast-entry forms and default categories such as food, transport, rent, utilities, shopping, and health.

### Acceptance criteria

Transactions can be added, edited, filtered, and found.

Transfers affect balances but are not counted as income or expenses.

Amount, account ownership, category, and date are validated server-side.

Duplicate submission and edit behavior are tested.

Loading, empty, validation, and error states are present.

Dependencies: Sprint 2 accounts.

## Sprint 4 — Income sources and recurring items

Weeks 7–8 | Usable outcome: A user can track multiple income sources and recurring transactions.

### Scope and deliverables

Support salary, rent, freelance, business, cash, and custom sources.

Create recurring rules for salary, rent, subscriptions, bills, and supported entries.

Allow items to be marked received/paid and prevent duplicate postings.

Build an Income page with source history and clearly labeled balances.

### Acceptance criteria

Multiple income sources can be managed.

Recurring entries follow schedules without accidental duplicates.

Period income is distinct from current account/source balance.

Total Balance definition is documented and tested.

Dependencies: Sprints 2–3 account and transaction models.

## Sprint 5 — Dashboard and analytics

Weeks 9–10 | Usable outcome: A user can understand finances through real, date-filtered data.

### Scope and deliverables

Show total balance, income, expenses, net cash flow, and recent transactions.

Add daily, weekly, monthly, yearly, and custom date-range views.

Add category spending charts, income-versus-expense trends, and period comparisons.

Provide useful first-run empty states and links to filtered transactions.

### Acceptance criteria

Metrics reconcile to underlying transactions/accounts.

Date filters handle month/year boundaries and user time zone.

Dashboard metrics match corresponding reports.

Charts do not imply data exists when it does not.

Web MVP can be deployed for controlled user testing.

Dependencies: Sprints 2–4 data and calculation rules.

## Sprint 6 — Budgets and savings goals

Weeks 11–12 | Usable outcome: A user can plan a purchase and understand the savings required.

### Scope and deliverables

Create monthly category budgets and progress indicators.

Create goals for travel, car, bike, home, emergency fund, and custom goals.

Capture target amount, target date, current saved amount; calculate monthly savings.

Add budget warnings, starting with in-app alerts if notification infrastructure is not ready.

### Acceptance criteria

Goal progress and monthly target calculations are tested.

Users can edit/archive goals without damaging transaction history.

Budget indicators use correct period and categories.

Assumptions are shown when a goal lacks a target date.

Dependencies: Sprint 5 reporting and validated calculations.

## Sprint 7 — Investment portfolio

Weeks 13–14 | Usable outcome: A user can record holdings and see portfolio composition and performance estimates.

### Scope and deliverables

Support shares/stocks, mutual funds, ETFs, deposits, and custom assets.

Record units, purchase price/cost basis, fees, history, and valuation date.

Show invested amount, current value, unrealized gain/loss, and asset allocation.

Allow manual valuation updates and distinguish manual, delayed, and live values.

### Acceptance criteria

Portfolio totals reconcile to included holdings.

Gain/loss assumptions are documented and tested.

Valuation timestamp and source are visible.

No live price is claimed without a trusted provider and timestamp.

Dependencies: Sprints 2 and 5 account/reporting foundations.

## Sprint 8 — Loans, liabilities and reports

Weeks 15–16 | Usable outcome: A user can see broader financial position and export records.

### Scope and deliverables

Track loans, credit-card liabilities, repayments, and EMI schedules.

Separate principal, interest, and fees where supported.

Add net worth and cash-flow history.

Provide CSV exports; PDF export is optional if time permits.

### Acceptance criteria

Net worth equals included assets minus included liabilities.

Repayments do not double-count principal as ordinary expenses where modeled separately.

Exports respect user permissions and date filters.

Exports cannot leak another user’s data.

Dependencies: Sprints 3, 5, and 7.

## Sprint 9 — AI-powered financial insights

Weeks 17–18 | Usable outcome: A user receives explanations grounded in verified financial data.

### Scope and deliverables

Summarize spending patterns and period-over-period changes.

Detect potential unusually high spending and budget overruns using deterministic checks first.

Generate savings scenarios based on goals and stated assumptions.

Add optional financial Q&A through a server-side provider abstraction.

Show context period, source figures, and links to relevant records.

### Acceptance criteria

Totals and comparisons are computed in validated code/SQL, not generated by AI.

Responses are bounded, validated, and labeled informational.

Only necessary summarized data is sent; secrets remain server-side.

Feature degrades gracefully if provider is unavailable.

AI cannot initiate payments, transfers, trades, or other financial actions.

Dependencies: Stable dashboard, goals, and portfolio data.

## Sprint 10 — Notifications and reminders

Weeks 19–20 | Usable outcome: A user can receive and control reminders across supported platforms.

### Scope and deliverables

Add optional daily 10 PM expense-entry reminder in the user’s time zone.

Allow time changes, opt-out, and preference management.

Add upcoming bill/EMI and recurring-transaction reminders where data exists.

Implement supported mobile push, supported web notifications, and in-app notification center.

Handle permission denial, token refresh, delivery errors, and time-zone changes.

### Acceptance criteria

Preferences persist and sync across devices.

Scheduling uses a reliable supported server-side mechanism.

Sensitive transaction details are not exposed on lock screens by default.

UI explains missing permissions or disabled notifications.

Do not promise exact delivery when OS/provider cannot guarantee it.

Dependencies: Sprints 1 and 4; notification infrastructure.

## Sprint 11 — Mobile polish, offline support and PWA

Weeks 21–22 | Usable outcome: The app is dependable across supported web and mobile workflows.

### Scope and deliverables

Polish mobile navigation, safe areas, keyboard behavior, loading states, and accessibility.

Add secure local caching and limited offline expense entry where feasible.

Queue offline changes with synchronization, idempotency, and conflict handling.

Make web installable as a PWA where supported.

Test session expiry, app lifecycle, push permissions, and cross-platform consistency.

### Acceptance criteria

Offline state is clear; unsynced data is not falsely reported as remotely saved.

Synchronization avoids duplicate transactions and handles conflicts.

Critical flows work on supported devices/browsers.

Accessibility and responsive checks are completed.

Dependencies: Stable core flows on web and mobile.

## Sprint 12 — Security, release and production readiness

Weeks 23–24 | Usable outcome: A tested release candidate is ready for deployment and store submission.

### Scope and deliverables

Run end-to-end tests for auth, expenses, transfers, reports, goals, and reminders.

Review RLS, authorization, rate limits, secrets, logs, and cross-user isolation.

Validate backups, recovery, migrations, monitoring, and performance.

Complete privacy policy, terms, account deletion, support contact, and store metadata.

Prepare web deployment and Android/iOS release builds.

### Acceptance criteria

Critical financial flows pass end-to-end tests.

Cross-user isolation tests pass for all user-owned data.

No known critical security issue remains open.

Production configuration and recovery steps are documented.

Release notes and store-submission materials are ready; store approval is not assumed.

Dependencies: All launch-critical features and environments.

# 5. Financial rules that must remain consistent

These are product invariants. Implement them in shared domain logic or trusted server-side code, and cover them with tests.

| Metric | Rule |
| --- | --- |
| Period income | Sum eligible income transactions in the selected period; not the same as current balance. |
| Period expenses | Sum eligible expenses in the period with documented refund/reversal handling. |
| Net cash flow | Period income minus period expenses; exclude transfers and avoid double counting. |
| Account balance | Opening balance plus posted inflows minus outflows, including transfers and balance-affecting events. |
| Net worth | Included assets minus included liabilities, with valuation dates defined. |
| Income page Total Balance | Bank Balance plus all other income-source balances, including Cash and other sources—not just bank plus cash if more sources exist. |
| Investment gain/loss | Current value minus cost basis, with explicit treatment of fees/distributions and valuation timestamps. |

Use integer minor units or PostgreSQL numeric for authoritative money calculations; avoid binary floating point.

Use the user’s time zone for day/week/month boundaries and scheduled reminders.

Transfers must not inflate income or expenses.

Prevent double-counting when funds move between accounts or a source is linked to an account.

Keep investment purchases distinct from ordinary expenses.

# 6. Definition of done for every sprint

Acceptance criteria are met and the feature works end to end.

Schema/migrations are version-controlled where applicable.

Server-side validation, authorization, and RLS are in place.

Financial formulas and date-boundary behavior have automated tests.

Loading, empty, error, retry, and success states exist where relevant.

Relevant tests, lint, typecheck, and build are run; failures are reported honestly.

No secrets or sensitive financial data leak into client code or logs.

Documentation/configuration is updated and feature is deployable to a safe test environment.

# 7. Key risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Scope expansion | Keep sprint scope fixed; add new ideas to a prioritized backlog. |
| Inconsistent balances | Canonical metrics, shared domain functions, database constraints, reconciliation tests. |
| Financial data exposure | RLS, server authorization, secret management, cross-user tests, careful logging from Sprint 1. |
| Market data costs | Start with manual valuations; assess coverage, licensing, freshness, and costs before integration. |
| AI hallucinations/privacy | Calculate in code, send minimal summaries, validate output, label suggestions. |
| Notification limits | Test each platform; communicate permissions and delivery limitations. |
| Offline conflicts | Limit offline scope; use idempotency and explicit pending/synced states. |
| App-store delays | Test mobile builds throughout; treat review approval as an external dependency. |

# 8. Release milestones

| When | Milestone | Exit condition |
| --- | --- | --- |
| End Sprint 2 | Account foundation | Authentication and account setup work; internal testing starts. |
| End Sprint 3 | Daily transaction ledger | Core expense tracking is usable. |
| End Sprint 5 | MVP / controlled web release | Auth, accounts, transactions, income, dashboard. |
| End Sprint 8 | Money management release | Goals, portfolio, liabilities, reports. |
| End Sprint 10 | Insights and reminders | AI and notifications behind appropriate controls. |
| End Sprint 12 | Production release candidate | Security, quality, deployment, and store-submission readiness. |

# 9. How to use Claude Code efficiently

Keep CLAUDE.md in the repository root as the stable source of product, architecture, security, and financial rules.

For each sprint prompt, name only the sprint and acceptance criteria; do not paste this entire plan every time.

Ask Claude to inspect existing code and relevant files before implementation.

Request a short plan, focused implementation, tests, and an honest completion report.

Do not let Claude silently start later sprints, rewrite architecture, add speculative dependencies, or deploy to production.

Update CLAUDE.md only when a durable decision changes; keep sprint-specific tasks in this plan or tickets.

# 10. Recommended first task

Ask Claude Code to inspect the repository and compare the current state with CLAUDE.md. Have it identify existing functionality, missing setup, migrations/auth risks, and the smallest safe Sprint 1 implementation plan. Then implement only Sprint 1. This reduces unnecessary rewrites and avoids building a second version of something that already works.

FIN CREADOR • Build small. Validate every sprint. Protect user trust.